## Project Timeline
Project Timeline
Line chart that plots each milestone on the corresponding timeframe is in this cell.
Project Milestones
Date | Milestone | Assigned To | Position | Baseline
2019-09-25 | Project Start |  | 10 | 0
2019-10-08 | Milestone 1 Start |  | 15 | 0
2019-10-09 | Standup Meeting | Project Planning | -10 | 0
2019-10-10 | Sprint 1 Start |  | 25 | 0
2019-10-13 | Weekly Scrum |  | -15 | 0
2019-10-16 | Standup Meeting | Sprint 2 Planning | 20 | 0
2019-10-17 | Sprint 2 Start |  | -12 | 0
2019-10-20 | Weekly Scrum |  | 15 | 0
2019-10-23 | Standup Meeting | Sprint 3 Planning | -20 | 0
2019-10-24 | Sprint 3 Start |  | 20 | 0
2019-10-27 | Weekly Scrum |  | -15 | 0
2019-10-30 | Standup Meeting | Requirement C Planning | 15 | 0
2019-11-03 | Weekly Scrun |  | 10 | 0
2019-11-05 | Presentation Finalization |  | -7 | 0
2019-11-06 | Milestone 1 End |  | 5 | 0